## Original
2020/21 TECHNICAL SERVICES AND INFRASTRUCTURE
IDP REF | KPI NO | NATIONAL KEY PERFORMANCE AREA(BACK TO BASIC PRINCIPLES) | Strategic goals | Strategic objectives | Strategies 2019/20 | Unit of measure | Key performance indicator (KPI) | BASELINE | BACKLOG | Annual Target | Annual budget | Source of Funding | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Reason for Varience | Corrective Measures | Portfolio of Evidence | WARD | Responsible department | Reason for adjustment
[13 empty] | Target | Target | Target | Target
BASIC SERVICE DELIVERY
BSD 05 | 1 | BASIC SERVICE DELIVERY (SERVICE DELIVERY: CREATING CONDITIONS FOR DECENT LIVING) | Universal access to basic services and infrastructure development by 2030 | Improve access to all infrastructure and services | Maintain a functional Infrastructure Development Programme Steering Committee (IDProgSC) | Number | Number of IDProgSC meeting to be held by 30 June 2021 | 1 | 1 | N/A | 0 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | Draft minutes of Meeting and Attendance register | N/A | TSID DIRECTOR | No budget inclusion for these meetings, please phase out.
BSD 06 | 2 |  |  |  | Maintain a functional Energy Forum | Number | Number of energy forum meetings to be held by 31 March 2021 | Not achieved | 1 | N/A | 0 | Municipal Operating Budget | N/A | N/A | N/A | N/A | N/A | N/A | Draft minutes of Meeting and Attendance register | N/A | TSID DIRECTOR
BSD 01 | 3 |  |  |  | Facilitate access to electricity for all targetted households | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 3A Ward 10 and ready for connection by 30 September 2020 | N/A | N/A | 211 | 5765139.76 | INEP | 211 | N/A | N/A | N/A | N/A | N/A | Signed progress report from Consultant | 10 | TSID DIRECTOR
BSD 01 | 4 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Nkwalini- Nkunzempunga and ready for connection by 30 September 2020 | N/A | N/A | 90 | 3734806.25 | INEP | 90 | N/A | N/A | N/A | N/A | N/A |  | 11,16
[7 empty] | Number of households to be provided with electrification infrastructure (Dry Connections) in eHlanzeni ward 7 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | 50 | 50 | N/A | N/A | Signed progress report from Consultant | 7 | TSID DIRECTOR | Tentative because the INEP budget has be decreased by department of Energy as of the 25-June-2020. from R6 000 000 to R5 000 000. The Annual targets are most likely to change as well.
[7 empty] | Number of households to be provided with electrification infrastructure (Dry Connections) in oKhovothi ward 12 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1640000 | INEP | N/A | N/A | 50 | 50 | N/A | N/A |  | 12
[7 empty] | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 4 ward 10 and ready for connection by 30 June 2020 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | 50 | 50 | N/A | N/A |  | 10
BSD 01 | 5 |  |  |  |  | Date | Date of fencing of the substation in Ward 3, Patrys Road by 30 November 2020 | Not achieved | 2019-06-30 | 2020-11-30 | 200000 | Municipal | N/A | 2020-11-30 | N/A | N/A | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR
BSD 01 | 6 |  |  |  |  | Number | Number of RMU's to be replaced by 31 December 2020 | Not achieved | 2020-12-31 | 3 | 1200000 | Municipal | N/A | 3 | N/A | N/A | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR
BSD 02 |  |  |  |  | Reduce the road infrastructure backlog and maintain the existing infrastructure | Number | Water Use Licence for the Nyoni taxi route Phase 4 by 31 December 2021 | N/A | N/A | 3.92km | 200000 | MIG/DOHS | N/A | N/A | N/A | 3.92km | N/A | N/A | Practical completion certificate | 10 | TSID DIRECTOR |  | Remove and defer to the next FY 21/22
BSD 02 | 7 |  |  |  |  | Date | Date of construction of Nyoni Phase 3 under-pass by 31 December 2020 | Achieved | 2019-03-10 | 2020-12-31 | 404000 | MIG/DOHS | N/A | N/A | 2020-03-31 | N/A | N/A | N/A | Practical completion certificate | 10,17. | TSID DIRECTOR | It was achieved and needs to be phased out
BSD 02 | 8 |  |  |  |  | Number | Number of km's of Enembe road to be completed and upgraded in wards 12,13,14 and 15 by 30 September 2020 | Not achieved | 1.8km | 1.8km | 7661452.66 | MIG | 1.8km | N/A | N/A | N/A | N/A | N/A | Practical completion certificate | 12,13,14 and 15 | TSID DIRECTOR
BSD 02 | 9 |  |  |  |  | Number | Number of kms of Link Road between Amajuba Road (Ward 15) and Road 116 (Ward 14) to be constructed and upgraded by 31 December 2020 | N/A | N/A | 0.35km | 3440757.69 | MIG | N/A | 0.35km | N/A | N/A | N/A | N/A | Award letter/ progress report | 14, 15 | TSID DIRECTOR
BSD 02 | 10 |  |  |  |  | Number | Number of kms of Link Road between Shayamoya Road (Ward 7) and Amajuba Road (Ward 15) to be constructed and upgraded by 31 December 2020 | N/A | N/A | 0.32km | 3019695.84 | MIG | N/A | 0.32km | N/A | N/A | N/A | N/A | Award letter/ progress report | 7, 15 | TSID DIRECTOR
BSD 02 | 11 |  |  |  |  | Number | Number of kms of Link Road between Masomonce Bus Route (Ward 10) and Enembe/Isithebe Link Road (Ward 12) to be constructed and upgraded by 30 June 2021 | N/A | N/A | 0.8km | 6762817.44 | MIG | N/A | N/A | N/A | 0.8km | N/A | N/A | Award letter/ progress report | 10, 12 | TSID DIRECTOR
[6 empty] | Percentage | Percentage of upgrade of 6.85kms for the Rural Road Upgrade Phase 3(A, B & C)in wards 2, 3 & 12 by 30 June 2021 | N/A | N/A | 100% | 1081757.69 | MIG | N/A | N/A | 100% (Tender Advert) | 100% contractor appointment | N/A | N/A | Advert/ Tender Award | 2, 3 & 12
BSD 02 | 12 |  |  |  |  | Number | Number of m2 potholes repaired on urban roads by 30 June 2021 | 1317.76 m² | 682.24 m² | 3000m² | 1500000 | Municipal | 600m² | 1000m² | 1000m² | 400m² | N/A | N/A | Measurement Reports | 2,3,4,7,10,12,13,14,15. | TSID DIRECTOR
BSD 02 | 13 |  |  |  |  | Number | Number of guard rails to be constructed by 31 March 2021 | Not achieved | 300m | 300m | 250000 | Municipal | N/A | N/A | 300m | N/A | N/A | N/A | Completion Certificate | 4,6,10 | TSID DIRECTOR
BSD 02 | 14 |  |  |  |  | Number | Number of kerbs and concrete channel to be constructed by 30 June 2021 | Not achieved | 250m | 200m | 50000 | Municipal | 80m | N/A | 60m | 60m | N/A | N/A | Measurement Reports | 4,6,10 | TSID DIRECTOR
BSD 02 | 15 |  |  |  |  | Number | Number of headwalls to be constructed by 31 December 2020 | Not achieved | 25 | 25 | 400000 | Municipal | N/A | 25 | N/A | N/A | N/A | N/A | Completion Certificate | 1,2,3,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR
BSD 02 | 16 |  |  |  |  | Number | Number of kilometres of rural gravel roads repaired and maintained in-house by 30 June 2021 | 324.9 km | None | 250 km | 2000000 | Municipal | 50km | 40km | 80km | 80km | N/A | N/A | Measurement Reports | 1,2,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR
[6 empty] | Date | Date of completion for Highview Park Stormwater modification by 30 June 2021 | N/A | N/A | 2021-06-30 | 800000 | Municipal | N/A | N/A | N/A | 2021-06-30 | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
BSD 02 | 17 |  |  |  |  | Number | Number of speed humps constructed by 31 December 2020 | Not achieved | 15 | 15 | 300000 | Municipal | N/A | 15 | N/A | N/A | N/A | N/A | Completion Certificate | 3,7,13,14,15. | TSID DIRECTOR
BSD 02 | 18 |  |  |  |  | Number | Number of temporal security guardhouses to be supplied and delivered in various sites (2.4m x 2.4m) by 30 June 2020 | N/A | N/A | 10 | 250000 | Municipal | N/A | N/A | N/A | 10 | N/A | N/A | Completion Certificate, delivery note/ pictures | 1,2,18 | TSID DIRECTOR | The National Lockdown led to the delay in procurement an appointment process of service providers. This was not predicted as the lockdown took place upruptly after the budget draft from T/S was handed in. though not achieved, it was not budgeted for 2020/21 FY. please phase out.
BSD 02 | 19 |  |  |  |  | Date | Date of Installation of 30 road signs and repainting of 15km of road markings to completed by the 31 March 2021 | Not achieved | 10 | 2021-03-31 | 400000 | Municipal | N/A | N/A | 2021-03-31 | N/A | N/A | N/A | Completion Certificate | 3,4,7,13,14,15. | TSID DIRECTOR
BSD 07 | 21 |  |  |  |  | Date | Date of completion of overlaying of top suface in Spar parking area in Ward 3 by 30 June 2021 | N/A | N/A | 2021-06-30 | 700000 | Municipal | N/A | N/A | N/A | 2021-06-30 | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR
BSD 02 | 20 |  |  |  |  | Number | Number of installed street name signage by 31 March 2021 | N/A | N/A | 30 | 130000 | Municipal | N/A | N/A | 30 | N/A | N/A | N/A | Measurement Reports | 3,7,13 | TSID DIRECTOR
BSD 07 | 21 |  | PROVIDING AND FACILITATING ACCESS TO SOCIAL SERVICES AND FACILITIES |  | Facilitate the provision of new community facilities | Percentage | Percentage of contractor appointment and the completion of construction for the swimming pool in ward 15 by 30 June 2021 | Not achieved | 100% (tender award) | 100% | 2870207.52 | MIG | 100% (tender award) | N/A | N/A | 100% Contruction completion | N/A | N/A | Tender award letter/ Practical Completion Certificate | 15 | TSID DIRECTOR
[6 empty] | Percentage | Planning stage fro stage 1-3 (Registration and Detailed design) for the sports field in Hlomendlini in Ward 4 by 30 June 2021 | N/A | N/A | 100% | 500000 | MIG | N/A | N/A | N/A | Notification of Registration (NOR) with MIG | N/A | N/A | Copy of the NOR letter from COGTA. | 4
[6 empty] | Percentage | Percentage of contractor appointment and the completion of construction for the sports field in Enembe in Ward 5 by 30 June 2021 | N/A | N/A | 100% | 6000000 | MIG | 100% (tender award) | N/A | N/A | 100% Contruction completion | N/A | N/A | Tender award letter/ Practical Completion Certificate | 5
[6 empty] | Date | Date of installation of recreational playpark facilities at ward 4 by 30 June 2020 | Not achieved | 2019-06-30 | 2020-06-30 | 800000 | MIG | N/A | N/A | N/A | 2020-06-30 | N/A | N/A | AFA with the council resolution/Minutes and advert/ tender award/Practical completion certificate | 4 | TSID DIRECTOR | COGTA advised to recommision the play park and re register the project. | To be removed from the Scorecard 20/21
BSD 07 | 22 |  |  |  |  | Date | Date of upgrading of Love Life centre by 30 September 2020 | N/A | N/A | 2020-09-30 | 450000 | Municipal | 2020-09-30 | N/A | N/A | N/A | N/A | N/A | Completion Certificate | 7 | TSID DIRECTOR
BSD 07 | 23 |  |  |  |  | Percentage | 50% percent construction progress and appointment of the contractor for construction for DLTC phase 1 by 30 June 2021 | N/A | N/A | 100% | 4000000 | Municipal | 100% (Award letter to contractor) | N/A | N/A | N/A | N/A | N/A | Award Letter | Ward 3 | TSID DIRECTOR
MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM 01 | 24 | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | TO DEVELOP A SUSTAINABLE AND EFFICIENT MUNICIPALITY BASED ON SOUND FINANCIAL MANAGEMENT | Ensure a financially viable municipality | Ensure a constant and accurate financial reporting | Number | Number of quarterly risk reports by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | Attendence register, updated risk register and/or letter of acknowledgent | N/A | TSID DIRECTOR
MFVM 02 | 25 |  |  |  | Improve audit opinion | Number | Number of quarterly review of A.G Action Plan by council by 30 June 2021 | 2 | 2 | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | Council resolution adopting the quarterly reviewed action plan | N/A | TSID DIRECTOR
MFVM 02 | 26 |  |  |  |  | Number | Number of Quarterly Internal Audit Responses provided to Internal Audit Unit by 30 June 2021 | 4 | None | 1 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID DIRECTOR
MFVM 06 | 27 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of 12 Cubic Meter Truck by 31 March 2021 | N/A | N/A | 2021-03-31 | N/A | N/A | N.A | N/A | 2021-03-31 | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR
MFVM 06 | 27 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of a Tar Mixer by 31 December 2020 | N/A | N/A | 2020-12-31 | N/A | N/A | N.A | 2020-12-31 | N/A | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR
MFVM 06 | 27 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of single drum roller by 30 June 2020 | N/A | N/A | 2020-03-31 | N/A | N/A | N.A | N/A | 2020-03-31 | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR | PHASE OUT, IT HAS BEEN ACHIEVED.
MFVM 07 | 28 |  |  |  | Ensure IDP alligned to financial planning | Date | Date of completing draft Departmental Budget estimate document by 28 February 2021 | 2020-03-03 | None | 2021-02-28 | N/A | N/A | N/A | N/A | 2021-02-28 | N/A | N/A | N/A | Draft budget estimate document | N/A | TSID DIRECTOR
MFVM 04 | 29 |  |  |  | Effectively and efficiently manage the expenditure of the municipality | Percentage | Percentage of expenditure on INEP funding by 30 June 2021 | N/A | N/A | 100% | 5000000 | INEP | 15% | 35% | 60% | 100% | N/A | N/A | Signed Report of Expenditure by the Department | N/A | TSID DIRECTOR
MFVM 04 | 30 |  |  |  |  | Percentage | Percentage of expenditure on MIG funding by 30 June 2021 | 99.9% | None | 100% | 35150000 | MIG | 19% | 41% | 66% | 100% | N/A | N/A | MIG Certificate of Expenditure and revenue | N/A | TSID DIRECTOR
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
GGPP 02 | 31 | Good governance and public participation | Ensure partcipative, transparent and accountable governance | Ensure participative, transparent and accountable governance | Ensure the existence and functionality of the public participation structures | Number | Number of quarterly clusters war room reports submitted to EXCO by 30 June 2021 | N/A | N/A | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | Signed quarterly reports | N/A | TSID DIRECTOR |  | Phase out
GGPP 02 | 32 |  |  |  |  | Number | Number of quarterly District IGR meetings attended by 30 June 2021 | 1 | 3 | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | Attendence register | N/A | TSID DIRECTOR
MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID 01 | 33 | Municipal transformation and institutional development | PROVISION OF EFFECTIVE, EFFICIENT, TRANSPARENT AND ACCOUNTABLE LEADERSHIP | Creating a conducive working environment | Maintain and improve the municipal policies | Date | Date of the development of the Building and Community Facilities maintenance plan by 30 June 2020 | N/A | N/A | 2020-06-30 | 200000 | Municipal | N/A | N/A | N/A | 2020-06-30 | N/A | N/A | Draft of Building and Community services plan. | N/A | TSID DIRECTOR |  | No Budget
MTID 02 | 34 |  |  |  | Ensure effective and efficient human resource management | Date | Date of submission of the departmental Organogram to Corporate Services Department for inclusion in the overall municipal organogram by 28 February 2021 | 2020-02-24 | None | 2021-02-28 | N/A | N/A | N/A | N/A | 2021-02-28 | N/A | N/A | N/A | Draft Organogram and Transmittal to CS/ Council resolution | N/A | TSID DIRECTOR
MTID 05 | 35 |  |  |  | Improve information technology and document management systems | Number | Number of quarterly IT steering committee meetings to attend by 30 June 2021 | 4' | None | 1900-01-03 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | Agenda and attendance register | N/A | TSID/DIRECTOR TSID |  | Phase out
MTID 06 | 36 |  |  |  | Maintain and improve municipal buildings and assets | Date | Date of partitioning of the Council Chamber by 31 March 2021 | 2019-12-31 | N/A | 2021-03-31 | 600000 | Municipal | N/A | N/A | 2021-03-31 | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
[6 empty] | Date | Date of fencing and gates at the Municipal offices (Main) by 31 March 2021 | N/A | N/A | 2021-03-31 | 250000 | Municipal | N/A | N/A | 2021-03-31 | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
MTID 06 | 37 |  |  |  |  | Number | Number of Municipal Plant and Equipment Serviced by 31 March 2021 | 4 | None | 4 | 3500000 | Municipal | N/A | N/A | 4 | N/A | N/A | N/A | Job Cards signed by Mechanic | N/A | TSID DIRECTOR
MTID 06 | 38 |  |  |  |  | Number | Number of Municipal Truck's COF and serviced by 30 June 2021 | 11 | None | 11 | 750000 | Municipal | 3 | 2 | 1 | 5 | N/A | N/A | COF Certificate with Job Card | N/A | TSID DIRECTOR
MTID 04 | 39 |  |  |  | Improve performance | Number | Number of monthly progress reports on implementation of performance plans by managers submitted to HOD's by 30 June 2021 | 12 | None | 12 | N/A | N/A | 3 | 3 | 3 | 3 | N/A | N/A | Monthly performance report | N/A | TSID/DIRECTOR TSID
MTID 04 | 40 |  |  |  |  | Date | Date of submission of manager's performance plan to HOD by 31 July 2020 | 2019-08-31 | N/A | 2020-07-31 | N/A | N/A | 2020-07-31 | N/A | N/A | N/A | N/A | N/A | Signed Manager's Performance Plan | N/A | TSID/DIRECTOR TSID
MTID 04 | 41 |  |  |  |  | Number | Number of completed quarterly PMS information (POE file and signed scorecard) to PMS unit by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | 1 | 1' | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID/DIRECTOR TSID
LOCAL ECONOMIC DEVELOPMENT
LED 02 | 42 | LOCAL ECONOMIC DEVELOPMENT | Promoting and facilitating human development | Achieve a holistic human development and capacitation for the realisation of a skilled employable workforce | Improve the community skills base | Date | Ensuring that all qualifying tender specifications provide for subcontracting opportunities for emerging local contractors as and when a tender document is being compiled by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | 2020-06-30 | N/A | N/A | Copy of the signed/ published tender advert. | N/A | TSID/DIRECTOR TSID
LED 02 | 43 |  |  |  |  | Date | Date of ensuring that project implementation includes employment of local labour as and when projects are implemented by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | 2020-06-30 | N/A | N/A | Reports for projects under construction. | N/A | TSID/DIRECTOR TSID
[19 empty] | Signature: | …………………………………..
KP GUMEDE
Director: TSID
Note on L46: Khetha Gumede: Correct the budget

## Quarter 1
2020/21 TECHNICAL SERVICES AND INFRASTRUCTURE
IDP REF | KPI NO | NATIONAL KEY PERFORMANCE AREA(BACK TO BASIC PRINCIPLES) | Strategic goals | Strategic objectives | Strategies 2019/20 | Unit of measure | Key performance indicator (KPI) | BASELINE | BACKLOG | Annual Target | Annual budget | Source of Funding | Quarter 1 | Quarter 1 | Reason for Varience | Corrective Measures | Portfolio of Evidence | WARD | Responsible department
[13 empty] | Target | Actual
BASIC SERVICE DELIVERY
BSD 01 | 1 |  |  |  | Facilitate access to electricity for all targetted households | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 3A Ward 10 and ready for connection by 30 September 2020 | N/A | N/A | 211 | 5765139.76 | INEP | 211 | 211 | N/A | N/A | Signed progress report from Consultant | 10 | TSID DIRECTOR
BSD 01 | 2 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Nkwalini- Nkunzempunga (ward 11 & 16) and ready for connection by 30 September 2020 | N/A | N/A | 90 | 3734806.25 | INEP | 90 | 90 | N/A | N/A |  | 11,16
| 3 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in eHlanzeni ward 7 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | N/A | N/A | Signed progress report from Consultant | 7 | TSID DIRECTOR
| 4 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in oKhovothi ward 12 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1640000 | INEP | N/A | N/A | N/A | N/A |  | 12
| 5 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 4 ward 10 and ready for connection by 30 June 2020 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | N/A | N/A |  | 10
BSD 01 | 6 |  |  |  |  | Date | Date of fencing of the substation in Ward 3, Patrys Road by 30 November 2020 | Not achieved | 2019-06-30 | 2020-11-30 | 200000 | Municipal | N/A | N/A | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR
BSD 01 | 7 |  |  |  |  | Number | Number of RMU's to be replaced by 31 December 2020 | Not achieved | 2020-12-31 | 3 | 1200000 | Municipal | N/A | N/A | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR
BSD 02 | 8 |  |  |  |  | Number | Number of km's of Enembe road to be completed and upgraded in wards 12,13,14 and 15 by 30 September 2020 | Not achieved | 1.8km | 1.8km | 7661452.66 | MIG | 1.8km | Not Achieved | The scope of work for Enembe entailed the constuction of pavement layers, kerbing, channeling, streetlighting, speedhumps, road marking and signage. The main contractor has reached a 100% completion on pavement, speedhumps and road markings. The outstanding work will be completed by Sub- contractors. Delay with appointment of Sub-contractors.Due to interference by Local Business Forums. | The Technical Services department took an initiative to draft a policy to assist the LED office to guide the process of appointing sub- contractor. Though the contruction of the road (1.8km)has been completed but the Practical completion could not be produced since there are still outstanding works to be done by the sub contractors. | Practical completion certificate | 12,13,14 and 15 | TSID DIRECTOR
BSD 02 | 9 |  |  |  |  | Number | Number of kms of Link Road between Amajuba Road (Ward 15) and Road 116 (Ward 14) to be constructed and upgraded by 31 December 2020 | N/A | N/A | 0.35km | 3440757.69 | MIG | N/A | N/A | N/A | N/A | Award letter/ progress report | 14, 15 | TSID DIRECTOR
BSD 02 | 10 |  |  |  |  | Number | Number of kms of Link Road between Shayamoya Road (Ward 7) and Amajuba Road (Ward 15) to be constructed and upgraded by 31 December 2020 | N/A | N/A | 0.32km | 3019695.84 | MIG | N/A | N/A | N/A | N/A | Award letter/ progress report | 7, 15 | TSID DIRECTOR
BSD 02 | 11 |  |  |  |  | Number | Number of kms of Link Road between Masomonce Bus Route (Ward 10) and Enembe/Isithebe Link Road (Ward 12) to be constructed and upgraded by 30 June 2021 | N/A | N/A | 0.8km | 6762817.44 | MIG | N/A | N/A | N/A | N/A | Award letter/ progress report | 10, 12 | TSID DIRECTOR
| 12 |  |  |  |  | Percentage | Percentage of upgrade of 6.85kms for the Rural Road Upgrade Phase 3(A, B & C)in wards 2, 3 & 12 by 30 June 2021 | N/A | N/A | 100% | 1081757.69 | MIG | N/A | N/A | N/A | N/A | Advert/ Tender Award | 2, 3 & 12
BSD 02 | 13 |  |  |  |  | Number | Number of m2 potholes repaired on urban roads by 30 June 2021 | 1317.76 m² | 682.24 m² | 3000m² | 1500000 | Municipal | 600m² | 97.3m² | Taxi disputes interrupted the Unit's services. The Municipality's plant was threathened. And a month was lost. Inclement weather conditions. | Work has resumed and trying to push as much since the rainy season is coming. | Measurement Reports | 2,3,4,7,10,12,13,14,15. | TSID DIRECTOR
BSD 02 | 14 |  |  |  |  | Number | Number of guard rails to be constructed by 31 March 2021 | Not achieved | 300m | 300m | 250000 | Municipal | N/A | N/A | N/A | N/A | Completion Certificate | 4,6,10 | TSID DIRECTOR
BSD 02 | 15 |  |  |  |  | Number | Number of kerbs and concrete channel to be constructed by 30 June 2021 | Not achieved | 250m | 200m | 50000 | Municipal | 80m | 0m | There were some internal delays from SCM. A requisition for materials had to be redone in 2020/21, while it was first done in 2019/20. material was received in September. | Work on kerbs has been started. The unit will push to cover both quarter 1 & 2 targets to be achieved by December. | Measurement Reports | 4,6,10 | TSID DIRECTOR
BSD 02 | 16 |  |  |  |  | Number | Number of headwalls to be constructed by 31 December 2020 | Not achieved | 25 | 25 | 400000 | Municipal | N/A | N/A | N/A | N/A | Completion Certificate | 1,2,3,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR
BSD 02 | 17 |  |  |  |  | Number | Number of kilometres of rural gravel roads repaired and maintained in-house by 30 June 2021 | 324.9 km | None | 250 km | 2000000 | Municipal | 50km | 86.22km | The unit hired an additional plants in July and August due to a large amount of damaged rural gravel roads. | N/A | Measurement Reports | 1,2,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR
| 18 |  |  |  |  | Date | Date of completion for Highview Park Stormwater modification by 30 June 2021 | N/A | N/A | 2021-06-30 | 800000 | Municipal | N/A | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
BSD 02 | 19 |  |  |  |  | Number | Number of speed humps constructed by 31 December 2020 | Not achieved | 15 | 15 | 300000 | Municipal | N/A | N/A | N/A | N/A | Completion Certificate | 3,7,13,14,15. | TSID DIRECTOR
BSD 02 | 20 |  |  |  |  | Date | Date of Installation of 30 road signs and repainting of 15km of road markings to completed by the 31 March 2021 | Not achieved | 10 | 2021-03-31 | 400000 | Municipal | N/A | N/A | N/A | N/A | Completion Certificate | 3,4,7,13,14,15. | TSID DIRECTOR
BSD 07 | 21 |  |  |  |  | Date | Date of completion of overlaying of top suface in Spar parking area in Ward 3 by 30 June 2021 | N/A | N/A | 2021-06-30 | 700000 | Municipal | N/A | N/A | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR
BSD 02 | 22 |  |  |  |  | Number | Number of installed street name signage by 31 March 2021 | N/A | N/A | 30 | 130000 | Municipal | N/A | N/A | N/A | N/A | Measurement Reports | 3,7,13 | TSID DIRECTOR
BSD 07 | 23 |  | PROVIDING AND FACILITATING ACCESS TO SOCIAL SERVICES AND FACILITIES |  | Facilitate the provision of new community facilities | Percentage | Percentage of contractor appointment and the completion of construction for the swimming pool in ward 15 by 30 June 2021 | Not achieved | 100% (tender award) | 100% | 2870207.52 | MIG | 100% (tender award) | 100% | Due to the National Lockdown the project could only be advertised in June. Thus delaying the process of the appointment of contractor. | Awarded on the 5th of October 2020 | Tender award letter/ Practical Completion Certificate | 15 | TSID DIRECTOR
| 24 |  |  |  |  | Percentage | Planning stage fro stage 1-3 (Registration and Detailed design) for the sports field in Hlomendlini in Ward 4 by 30 June 2021 | N/A | N/A | 100% | 500000 | MIG | N/A | N/A | N/A | N/A | Copy of the NOR letter from COGTA. | 4
| 25 |  |  |  |  | Percentage | Percentage of contractor appointment and the completion of construction for the sports field in Enembe in Ward 5 by 30 June 2021 | N/A | N/A | 100% | 6000000 | MIG | 100% (tender award) | 100% | Due to the National Lockdown the project could only be advertised in June. Thus delaying the process of the appointment of contractor. | Awarded on the 5th of October 2020 | Tender award letter/ Practical Completion Certificate | 5
BSD 07 | 26 |  |  |  |  | Date | Date of upgrading of Love Life centre by 30 September 2020 | N/A | N/A | 2020-09-30 | 450000 | Municipal | 2020-09-30 | 2020-09-30 | N/A | N/A | Completion Certificate | 7 | TSID DIRECTOR
BSD 07 | 27 |  |  |  |  | Percentage | 50% percent construction progress and appointment of the contractor for construction for DLTC phase 1 by 30 June 2021 | N/A | N/A | 100% | 4000000 | Municipal | 100% (Award letter to contractor) | Not Achieved | Due to the National Lockdown the project could only be advertised in June. Thus delaying the process of the appointment of contractor. | As soon as it was possible advertisement was done on the 4th of June 2020. And appointment is set to be done by the end of October. | Award Letter | Ward 3 | TSID DIRECTOR
MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM 01 | 28 | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | TO DEVELOP A SUSTAINABLE AND EFFICIENT MUNICIPALITY BASED ON SOUND FINANCIAL MANAGEMENT | Ensure a financially viable municipality | Ensure a constant and accurate financial reporting | Number | Number of quarterly risk reports by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | N/A | N/A | Attendence register, updated risk register and/or letter of acknowledgent | N/A | TSID DIRECTOR
MFVM 02 | 29 |  |  |  | Improve audit opinion | Number | Number of quarterly review of A.G Action Plan by council by 30 June 2021 | 2 | 2 | 4 | N/A | N/A | 1 | 1 | N/A | N/A | Council resolution adopting the quarterly reviewed action plan | N/A | TSID DIRECTOR
MFVM 02 | 30 |  |  |  |  | Number | Number of Quarterly Internal Audit Responses provided to Internal Audit Unit by 30 June 2021 | 4 | None | 1 | N/A | N/A | 1 | 1 | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID DIRECTOR
MFVM 06 | 31 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of 12 Cubic Meter Truck by 31 March 2021 | N/A | N/A | 2021-03-31 | N/A | N/A | N.A | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR
MFVM 06 | 32 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of a Tar Mixer by 31 December 2020 | N/A | N/A | 2020-12-31 | N/A | N/A | N.A | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR
MFVM 07 | 33 |  |  |  | Ensure IDP alligned to financial planning | Date | Date of completing draft Departmental Budget estimate document by 28 February 2021 | 2020-03-03 | None | 2021-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | Draft budget estimate document | N/A | TSID DIRECTOR
MFVM 04 | 34 |  |  |  | Effectively and efficiently manage the expenditure of the municipality | Percentage | Percentage of expenditure on INEP funding by 30 June 2021 | N/A | N/A | 100% | 5000000 | INEP | 15% | 19% | N/A | N/A | Signed Report of Expenditure by the Department | N/A | TSID DIRECTOR
MFVM 04 | 35 |  |  |  |  | Percentage | Percentage of expenditure on MIG funding by 30 June 2021 | 99.9% | None | 100% | 35150000 | MIG | 19% | 10% | Procurement processes were planned to be done in April to ensure construction commences between June and July. However, due to the National Lockdown the procurement processes could only resume in June. | When the country moved to level 3, where construction and suppliers could trade and work. The unit ensured the procurement processes were fast tracked as a result two projects have been provisionally awarded and one to be awarded by the end of October 2020. | MIG Certificate of Expenditure and revenue | N/A | TSID DIRECTOR
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
GGPP 02 | 36 |  |  |  |  | Number | Number of quarterly District IGR meetings attended by 30 June 2021 | 1 | 3 | 4 | N/A | N/A | 1 | 0 | No invitation was extended by the IGR organizers which is the District Ilembe. | N/A | Attendence register | N/A | TSID DIRECTOR
MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID 01 | 37 | Municipal transformation and institutional development | PROVISION OF EFFECTIVE, EFFICIENT, TRANSPARENT AND ACCOUNTABLE LEADERSHIP | Creating a conducive working environment | Maintain and improve the municipal policies | Date | Date of the development of the Building and Community Facilities maintenance plan by 30 June 2020 | N/A | N/A | 2020-06-30 | 200000 | Municipal | N/A | N/A | N/A | N/A | Draft of Building and Community services plan. | N/A | TSID DIRECTOR
MTID 02 | 38 |  |  |  | Ensure effective and efficient human resource management | Date | Date of submission of the departmental Organogram to Corporate Services Department for inclusion in the overall municipal organogram by 28 February 2021 | 2020-02-24 | None | 2021-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | Draft Organogram and Transmittal to CS/ Council resolution | N/A | TSID DIRECTOR
MTID 06 | 39 |  |  |  | Maintain and improve municipal buildings and assets | Date | Date of partitioning of the Council Chamber by 31 March 2021 | 2019-12-31 | N/A | 2021-03-31 | 600000 | Municipal | N/A | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
| 40 |  |  |  |  | Date | Date of fencing and gates at the Municipal offices (Main) by 31 March 2021 | N/A | N/A | 2021-03-31 | 250000 | Municipal | N/A | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
MTID 06 | 41 |  |  |  |  | Number | Number of Municipal Plant and Equipment Serviced by 31 March 2021 | 4 | None | 4 | 3500000 | Municipal | N/A | N/A | N/A | N/A | Job Cards signed by Mechanic | N/A | TSID DIRECTOR
MTID 06 | 42 |  |  |  |  | Number | Number of Municipal Truck's COF and serviced by 30 June 2021 | 11 | None | 11 | 750000 | Municipal | 3 | 3 | N/A | N/A | COF Certificate with Job Card | N/A | TSID DIRECTOR
MTID 04 | 43 |  |  |  | Improve performance | Number | Number of monthly progress reports on implementation of performance plans by managers submitted to HOD's by 30 June 2021 | 12 | None | 12 | N/A | N/A | 3 | 3 | N/A | N/A | Monthly performance report | N/A | TSID/DIRECTOR TSID
MTID 04 | 44 |  |  |  |  | Date | Date of submission of manager's performance plan to HOD by 31 July 2020 | 2019-08-31 | N/A | 2020-07-31 | N/A | N/A | 2020-07-31 | 2020-08-31 | N/A | N/A | Signed Manager's Performance Plan | N/A | TSID/DIRECTOR TSID
MTID 04 | 45 |  |  |  |  | Number | Number of completed quarterly PMS information (POE file and signed scorecard) to PMS unit by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID/DIRECTOR TSID
LOCAL ECONOMIC DEVELOPMENT
LED 02 | 46 | LOCAL ECONOMIC DEVELOPMENT | Promoting and facilitating human development | Achieve a holistic human development and capacitation for the realisation of a skilled employable workforce | Improve the community skills base | Date | Ensuring that all qualifying tender specifications provide for subcontracting opportunities for emerging local contractors as and when a tender document is being compiled by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | Copy of the signed/ published tender advert. | N/A | TSID/DIRECTOR TSID
LED 02 | 47 |  |  |  |  | Date | Date of ensuring that project implementation includes employment of local labour as and when projects are implemented by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | Reports for projects under construction. | N/A | TSID/DIRECTOR TSID
[17 empty] | Signature: | …………………………………..
KP GUMEDE
Director: TSID
Note on L39: Khetha Gumede: Correct the budget

## Quarter 2
2020/21 TECHNICAL SERVICES AND INFRASTRUCTURE
IDP REF | KPI NO | NATIONAL KEY PERFORMANCE AREA(BACK TO BASIC PRINCIPLES) | Strategic goals | Strategic objectives | Strategies 2019/20 | Unit of measure | Key performance indicator (KPI) | BASELINE | BACKLOG | Annual Target | Annual budget | Source of Funding | Quarter 1 | Quarter 1 | Quarter 2 | Quarter 2 | Mid- year | Mid- year | Reason for Varience | Corrective Measures | Portfolio of Evidence | WARD | Responsible department
[13 empty] | Target | Actual | Target | Actual | Target | Actual
BASIC SERVICE DELIVERY
BSD 01 | 1 |  |  |  | Facilitate access to electricity for all targetted households | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 3A Ward 10 and ready for connection by 30 September 2020 | N/A | N/A | 211 | 5765139.76 | INEP | 211 | 211 | N/A | N/A | 211 | 211 | N/A | N/A | Signed progress report from Consultant | 10 | TSID DIRECTOR
BSD 01 | 2 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Nkwalini- Nkunzempunga (ward 11 & 16) and ready for connection by 30 September 2020 | N/A | N/A | 90 | 3734806.25 | INEP | 90 | 90 | N/A | N/A | 90 | 90 | N/A | N/A |  | 11,16
| 3 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in eHlanzeni ward 7 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Signed progress report from Consultant | 7 | TSID DIRECTOR
| 4 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in oKhovothi ward 12 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1640000 | INEP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 12
| 5 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 4 ward 10 and ready for connection by 30 June 2020 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 10
BSD 01 | 6 |  |  |  |  | Date | Date of fencing of the substation in Ward 3, Patrys Road by 30 November 2020 | Not achieved | 2019-06-30 | 2020-11-30 | 200000 | Municipal | N/A | N/A | 2020-11-30 | Not Achieved | 2020-11-30 | Not Achieved | The project has been awarded in September 2020. There is a slow performance by contractor. | The service provider is being monitored closely and the contractor has committed to complete at the end of January 2021 | Completion Certificate | 3 | TSID DIRECTOR
BSD 01 | 7 |  |  |  |  | Number | Number of RMU's to be replaced by 31 December 2020 | Not achieved | 2020-12-31 | 3 | 1200000 | Municipal | N/A | N/A | 3 | 0 | 3 | 0 | The specification along with panel of contractors specification documents were submitted to SCM demand management section on the 15 September 2020 . | The Demand Management Unit has committed to include the specification in the first Bid Specification Committee seating in 2021. | Completion Certificate | 3 | TSID DIRECTOR
BSD 02 | 8 |  |  |  |  | Number | Number of km's of Enembe road to be completed and upgraded in wards 12,13,14 and 15 by 30 September 2020 | Not achieved | 1.8km | 1.8km | 7661452.66 | MIG | 1.8km | Not Achieved | N/A | N/A | 1.8km | Not Achieved | The scope of work for Enembe entailed the constuction of pavement layers, kerbing, channeling, streetlighting, speedhumps, road marking and signage. The main contractor has reached a 100% completion on pavement, speedhumps and road markings. The outstanding work will be completed by Sub- contractors. Delay with appointment of Sub-contractors.Due to interference by Local Business Forums. | The Technical Services department took an initiative to draft a policy to assist the LED office to guide the process of appointing sub- contractor. Though the contruction of the road (1.8km)has been completed but the Practical completion could not be produced since there are still outstanding works to be done by the sub contractors. | Practical completion certificate | 12,13,14 and 15 | TSID DIRECTOR
BSD 02 | 9 |  |  |  |  | Number | Number of kms of Link Road between Amajuba Road (Ward 15) and Road 116 (Ward 14) to be constructed and upgraded by 31 December 2020 | N/A | N/A | 0.35km | 3440757.69 | MIG | N/A | N/A | 0.35km | 0.35km | 0.35km | 0.35km | N/A | N/A | Award letter/ progress report | 14, 15 | TSID DIRECTOR
BSD 02 | 10 |  |  |  |  | Number | Number of kms of Link Road between Shayamoya Road (Ward 7) and Amajuba Road (Ward 15) to be constructed and upgraded by 31 December 2020 | N/A | N/A | 0.32km | 3019695.84 | MIG | N/A | N/A | 0.32km | 0.32km | 0.32km | 0.32km | N/A | N/A | Award letter/ progress report | 7, 15 | TSID DIRECTOR
BSD 02 | 11 |  |  |  |  | Number | Number of kms of Link Road between Masomonce Bus Route (Ward 10) and Enembe/Isithebe Link Road (Ward 12) to be constructed and upgraded by 30 June 2021 | N/A | N/A | 0.8km | 6762817.44 | MIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Award letter/ progress report | 10, 12 | TSID DIRECTOR
| 12 |  |  |  |  | Percentage | Percentage of upgrade of 6.85kms for the Rural Road Upgrade Phase 3(A, B & C)in wards 2, 3 & 12 by 30 June 2021 | N/A | N/A | 100% | 1081757.69 | MIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Advert/ Tender Award | 2, 3 & 12
BSD 02 | 13 |  |  |  |  | Number | Number of m2 potholes repaired on urban roads by 30 June 2021 | 1317.76 m² | 682.24 m² | 3000m² | 1500000 | Municipal | 600m² | 97.3m² | 1000m² | 228.7m² | 1600m² | 326m² | Taxi disputes interrupted the Unit's services. The Municipality's plant was threathened. And a month was lost. Inclement weather conditions. | Work has resumed and trying to push as much since the rainy season is coming. | Measurement Reports | 2,3,4,7,10,12,13,14,15. | TSID DIRECTOR
BSD 02 | 14 |  |  |  |  | Number | Number of guard rails to be constructed by 31 March 2021 | Not achieved | 300m | 300m | 250000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completion Certificate | 4,6,10 | TSID DIRECTOR
BSD 02 | 15 |  |  |  |  | Number | Number of kerbs and concrete channel to be constructed by 30 June 2021 | Not achieved | 250m | 200m | 50000 | Municipal | 80m | 0m | N/A | N/A | 80m | 0m | There were some internal delays from SCM. A requisition for materials had to be redone in 2020/21, while it was first done in 2019/20. material was received in September. | Work on kerbs has been started. The unit will push to cover both quarter 1 & 2 targets to be achieved by December. | Measurement Reports | 4,6,10 | TSID DIRECTOR
BSD 02 | 16 |  |  |  |  | Number | Number of headwalls to be constructed by 31 December 2020 | Not achieved | 25 | 25 | 400000 | Municipal | N/A | N/A | 25 | 15 | 25 | 15 | 25 headwalls were over formal quotation which is R200 000. Under the amount, the unit could manage to do 15. | The 10 will be done in the 3rd quarter. | Completion Certificate | 1,2,3,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR
BSD 02 | 17 |  |  |  |  | Number | Number of kilometres of rural gravel roads repaired and maintained in-house by 30 June 2021 | 324.9 km | None | 250 km | 2000000 | Municipal | 50km | 86.22km | 40km | 51.25km | 90km | 137.47km | The unit hired an additional plants in July and August due to a large amount of damaged rural gravel roads. | N/A | Measurement Reports | 1,2,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR
| 18 |  |  |  |  | Date | Date of completion for Highview Park Stormwater modification by 30 June 2021 | N/A | N/A | 2021-06-30 | 800000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
BSD 02 | 19 |  |  |  |  | Number | Number of speed humps constructed by 31 December 2020 | Not achieved | 15 | 15 | 300000 | Municipal | N/A | N/A | 15 | 15 | 15 | 15 | N/A | N/A | Completion Certificate | 3,7,13,14,15. | TSID DIRECTOR
BSD 02 | 20 |  |  |  |  | Date | Date of Installation of 30 road signs and repainting of 15km of road markings to completed by the 31 March 2021 | Not achieved | 10 | 2021-03-31 | 400000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completion Certificate | 3,4,7,13,14,15. | TSID DIRECTOR
BSD 07 | 21 |  |  |  |  | Date | Date of completion of overlaying of top suface in Spar parking area in Ward 3 by 30 June 2021 | N/A | N/A | 2021-06-30 | 700000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR
BSD 02 | 22 |  |  |  |  | Number | Number of installed street name signage by 31 March 2021 | N/A | N/A | 30 | 130000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Measurement Reports | 3,7,13 | TSID DIRECTOR
BSD 07 | 23 |  | PROVIDING AND FACILITATING ACCESS TO SOCIAL SERVICES AND FACILITIES |  | Facilitate the provision of new community facilities | Percentage | Percentage of contractor appointment and the completion of construction for the swimming pool in ward 15 by 30 June 2021 | Not achieved | 100% (tender award) | 100% | 2870207.52 | MIG | 100% (tender award) | 100% | N/A | N/A | 100% (tender award) | 100% | Due to the National Lockdown the project could only be advertised in June. Thus delaying the process of the appointment of contractor. | Awarded on the 5th of October 2020 | Tender award letter/ Practical Completion Certificate | 15 | TSID DIRECTOR
| 24 |  |  |  |  | Percentage | Planning stage fro stage 1-3 (Registration and Detailed design) for the sports field in Hlomendlini in Ward 4 by 30 June 2021 | N/A | N/A | 100% | 500000 | MIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Copy of the NOR letter from COGTA. | 4
| 25 |  |  |  |  | Percentage | Percentage of contractor appointment and the completion of construction for the sports field in Enembe in Ward 5 by 30 June 2021 | N/A | N/A | 100% | 6000000 | MIG | 100% (tender award) | 100% | N/A | N/A | 100% (tender award) | 100% | Due to the National Lockdown the project could only be advertised in June. Thus delaying the process of the appointment of contractor. | Awarded on the 5th of October 2020 | Tender award letter/ Practical Completion Certificate | 5
BSD 07 | 26 |  |  |  |  | Date | Date of upgrading of Love Life centre by 30 September 2020 | N/A | N/A | 2020-09-30 | 450000 | Municipal | 2020-09-30 | 2020-09-30 | N/A | N/A | 2020-09-30 | 2020-09-30 | N/A | N/A | Completion Certificate | 7 | TSID DIRECTOR
BSD 07 | 27 |  |  |  |  | Percentage | 50% percent construction progress and appointment of the contractor for construction for DLTC phase 1 by 30 June 2021 | N/A | N/A | 100% | 4000000 | Municipal | 100% (Award letter to contractor) | Not Achieved | N/A | N/A | 100% (Award letter to contractor) | Not Achieved | Due to the National Lockdown the project could only be advertised in June. Thus delaying the process of the appointment of contractor. | As soon as it was possible advertisement was done on the 4th of June 2020. And appointment is set to be done by the end of October. | Award Letter | Ward 3 | TSID DIRECTOR
MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM 01 | 28 | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | TO DEVELOP A SUSTAINABLE AND EFFICIENT MUNICIPALITY BASED ON SOUND FINANCIAL MANAGEMENT | Ensure a financially viable municipality | Ensure a constant and accurate financial reporting | Number | Number of quarterly risk reports by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | 1 | 1 | 2 | 2 | N/A | N/A | Attendence register, updated risk register and/or letter of acknowledgent | N/A | TSID DIRECTOR
MFVM 02 | 29 |  |  |  | Improve audit opinion | Number | Number of quarterly review of A.G Action Plan by council by 30 June 2021 | 2 | 2 | 4 | N/A | N/A | 1 | 1 | 1 | 0 | 2 | 1 | There was no sitting of the AG committee. The ruling was still the same as in the first quarter. | N/A | Council resolution adopting the quarterly reviewed action plan | N/A | TSID DIRECTOR
MFVM 02 | 30 |  |  |  |  | Number | Number of Quarterly Internal Audit Responses provided to Internal Audit Unit by 30 June 2021 | 4 | None | 1 | N/A | N/A | 1 | 1 | 1 | 1 | 2 | 2 | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID DIRECTOR
MFVM 06 | 31 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of 12 Cubic Meter Truck by 31 March 2021 | N/A | N/A | 2021-03-31 | N/A | N/A | N.A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR
MFVM 06 | 32 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of a Tar Mixer by 31 December 2020 | N/A | N/A | 2020-12-31 | N/A | N/A | N.A | N/A | 2020-12-31 | Not Achieved | 2020-12-31 | Not Achieved | The estimated amount for the small tar mixer was correct but after making an evaluation it was picked up that a big tax mixer is needed for thr workload. Which is over the estimated budget. Rather than to buy something that will not be effective. The team suggested at the adjustment budget maybe there can be a top up done to assist in purchasing the big tax mixer. | It will be put forward as one of the items that need fincial assistance from the items that still have money to share during the adjustment budget. | copy of invoice | N/A | TSID DIRECTOR
MFVM 07 | 33 |  |  |  | Ensure IDP alligned to financial planning | Date | Date of completing draft Departmental Budget estimate document by 28 February 2021 | 2020-03-03 | None | 2021-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Draft budget estimate document | N/A | TSID DIRECTOR
MFVM 04 | 34 |  |  |  | Effectively and efficiently manage the expenditure of the municipality | Percentage | Percentage of expenditure on INEP funding by 30 June 2021 | N/A | N/A | 100% | 5000000 | INEP | 15% | 19% | 35% | 6.48% | 50% | 25% | Poor performance of consultants | The Accounting Officer & Head of department has sent warning letters to the consultants to address their non performance. Working together they will try fast-track all works. | Signed Report of Expenditure by the Department | N/A | TSID DIRECTOR
MFVM 04 | 35 |  |  |  |  | Percentage | Percentage of expenditure on MIG funding by 30 June 2021 | 99.9% | None | 100% | 35150000 | MIG | 19% | 10% | 41% | 34% | 60% | 44% | Procurement processes were planned to be done in April to ensure construction commences between June and July. However, due to the National Lockdown the procurement processes could only resume in June. | When the country moved to level 3, where construction and suppliers could trade and work. The unit ensured the procurement processes were fast tracked as a result two projects have been provisionally awarded and one to be awarded by the end of October 2020. | MIG Certificate of Expenditure and revenue | N/A | TSID DIRECTOR
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
GGPP 02 | 36 |  |  |  |  | Number | Number of quarterly District IGR meetings attended by 30 June 2021 | 1 | 3 | 4 | N/A | N/A | 1 | 0 | 1 | 0 | 2 | 0 | In Q1 no invitation was extended by the IGR organizers which is the District Ilembe. In Q2 the meeting scheduled to sit on the 10th of December was cancelled until further notice by the IGR organizers. | N/A | Attendence register | N/A | TSID DIRECTOR
MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID 01 | 37 | Municipal transformation and institutional development | PROVISION OF EFFECTIVE, EFFICIENT, TRANSPARENT AND ACCOUNTABLE LEADERSHIP | Creating a conducive working environment | Maintain and improve the municipal policies | Date | Date of the development of the Building and Community Facilities maintenance plan by 30 June 2020 | N/A | N/A | 2020-06-30 | 200000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Draft of Building and Community services plan. | N/A | TSID DIRECTOR
MTID 02 | 38 |  |  |  | Ensure effective and efficient human resource management | Date | Date of submission of the departmental Organogram to Corporate Services Department for inclusion in the overall municipal organogram by 28 February 2021 | 2020-02-24 | None | 2021-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Draft Organogram and Transmittal to CS/ Council resolution | N/A | TSID DIRECTOR
MTID 06 | 39 |  |  |  | Maintain and improve municipal buildings and assets | Date | Date of partitioning of the Council Chamber by 31 March 2021 | 2019-12-31 | N/A | 2021-03-31 | 600000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
| 40 |  |  |  |  | Date | Date of fencing and gates at the Municipal offices (Main) by 31 March 2021 | N/A | N/A | 2021-03-31 | 250000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR
MTID 06 | 41 |  |  |  |  | Number | Number of Municipal Plant and Equipment Serviced by 31 March 2021 | 4 | None | 4 | 3500000 | Municipal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Job Cards signed by Mechanic | N/A | TSID DIRECTOR
MTID 06 | 42 |  |  |  |  | Number | Number of Municipal Truck's COF and serviced by 30 June 2021 | 11 | None | 11 | 750000 | Municipal | 3 | 3 | 2 | 2 | 5 | 5 | N/A | N/A | COF Certificate with Job Card | N/A | TSID DIRECTOR
MTID 04 | 43 |  |  |  | Improve performance | Number | Number of monthly progress reports on implementation of performance plans by managers submitted to HOD's by 30 June 2021 | 12 | None | 12 | N/A | N/A | 3 | 3 | 3 | 3 | 6 | 6 | N/A | N/A | Monthly performance report | N/A | TSID/DIRECTOR TSID
MTID 04 | 44 |  |  |  |  | Date | Date of submission of manager's performance plan to HOD by 31 July 2020 | 2019-08-31 | N/A | 2020-07-31 | N/A | N/A | 2020-07-31 | 2020-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | Signed Manager's Performance Plan | N/A | TSID/DIRECTOR TSID
MTID 04 | 45 |  |  |  |  | Number | Number of completed quarterly PMS information (POE file and signed scorecard) to PMS unit by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | 1 | 1 | 2 | 2 | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID/DIRECTOR TSID
LOCAL ECONOMIC DEVELOPMENT
LED 02 | 46 | LOCAL ECONOMIC DEVELOPMENT | Promoting and facilitating human development | Achieve a holistic human development and capacitation for the realisation of a skilled employable workforce | Improve the community skills base | Date | Ensuring that all qualifying tender specifications provide for subcontracting opportunities for emerging local contractors as and when a tender document is being compiled by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Copy of the signed/ published tender advert. | N/A | TSID/DIRECTOR TSID
LED 02 | 47 |  |  |  |  | Date | Date of ensuring that project implementation includes employment of local labour as and when projects are implemented by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Reports for projects under construction. | N/A | TSID/DIRECTOR TSID
[21 empty] | Signature: | …………………………………..
KP GUMEDE
Director: TSID
Note on L39: Khetha Gumede: Correct the budget

## Adjusted
2020/21 TECHNICAL SERVICES AND INFRASTRUCTURE ADJUSTED SCORECARD
IDP REF | KPI NO | NATIONAL KEY PERFORMANCE AREA(BACK TO BASIC PRINCIPLES) | Strategic goals | Strategic objectives | Strategies 2020/21 | Unit of measure | Key performance indicator (KPI) | BASELINE | BACKLOG | Annual Target | Annual budget | Source of Funding | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Reason for Varience | Corrective Measures | Portfolio of Evidence | WARD | Responsible department | Adjustments
[13 empty] | Target | Target | Target | Target
BASIC SERVICE DELIVERY
BSD 01 | 1 |  |  |  | Facilitate access to electricity for all targetted households | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 3A Ward 10 and ready for connection by 30 September 2020 | N/A | N/A | 211 | 5765139.76 | INEP | 211 | N/A | N/A | N/A | N/A | N/A | Signed progress report from Consultant | 10 | TSID DIRECTOR | No adjustment
BSD 01 | 2 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Nkwalini- Nkunzempunga (ward 11 & 16) and ready for connection by 30 September 2020 | N/A | N/A | 90 | 3734806.25 | INEP | 90 | N/A | N/A | N/A | N/A | N/A |  | 11,16 |  | No adjustment
BSD 01 | 3 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in eHlanzeni ward 7 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | N/A | 100 | N/A | N/A | Signed progress report from Consultant | 7 | TSID DIRECTOR | Move the 50 3rd quarter to the 4th quarter. Which then means 4th quarter target will be 100. Due to consultant's delay
BSD 01 | 4 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in oKhovothi ward 12 and ready for connection by 30 June 2021 | N/A | N/A | 100 | 1640000 | INEP | N/A | N/A | N/A | 100 | N/A | N/A |  | 12 |  | Move the 50 3rd quarter to the 4th quarter. Which then means 4th quarter target will be 100. Due to consultant's delay
BSD 01 | 5 |  |  |  |  | Number | Number of households to be provided with electrification infrastructure (Dry Connections) in Khenana Phase 4 ward 10 and ready for connection by 30 June 2020 | N/A | N/A | 100 | 1680000 | INEP | N/A | N/A | N/A | 100 | N/A | N/A |  | 10 |  | Move the 50 3rd quarter to the 4th quarter. Which then means 4th quarter target will be 100. Due to consultant's delay
BSD 01 | 6 |  |  |  |  | Date | Date of fencing of the substation in Ward 3, Patrys Road by 28 February 2021 | Not achieved | 2019-06-30 | 2021-02-28 | 200000 | Municipal | N/A | N/A | 2021-02-28 | N/A | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR | Target date to be moved to 28 Feb 2021, which is the 3rd quarter. Due to the contractor delay. The contractor was given P.O in September but the contractor took a while to start and comlete the job.
BSD 01 | 7 |  |  |  |  | Number | Number of RMU's to be replaced by 31 December 2020 | Not achieved | 2020-12-31 | 3 | 1200000 | Municipal | N/A | N/A | N/A | 3 | N/A | N/A | Completion Certificate | 3 | TSID DIRECTOR | Move 3 RMU installation to 4th quarter.
BSD 02 | 8 |  |  |  | Reduce the road infrastructure backlog and maintain the existing infrastructure | Number | Number of km's of Enembe road to be completed and upgraded in wards 12,13,14 and 15 by 30 September 2020 | Not achieved | 1.8km | 1.8km | 7661452.66 | MIG | 1.8km | N/A | N/A | N/A | N/A | N/A | Practical completion certificate | 12,13,14 and 15 | TSID DIRECTOR | No adjustment
BSD 02 | 9 |  |  |  |  | Number | Number of kms of Link Road between Amajuba Road (Ward 15) and Road 116 (Ward 14) to be constructed and upgraded to black top by 31 December 2020 | N/A | N/A | 0.35km | 3440757.69 | MIG | N/A | 0.35km | N/A | N/A | N/A | N/A | Award letter/ progress report | 14, 15 | TSID DIRECTOR | No adjustment
BSD 02 | 10 |  |  |  |  | Number | Number of kms of Link Road between Shayamoya Road (Ward 7) and Amajuba Road (Ward 15) to be constructed and upgraded to black top by 31 December 2020 | N/A | N/A | 0.32km | 3019695.84 | MIG | N/A | 0.32km | N/A | N/A | N/A | N/A | Award letter/ progress report | 7, 15 | TSID DIRECTOR | No adjustment
BSD 02 | 11 |  |  |  |  | Number | Number of kms of Link Road between Masomonce Bus Route (Ward 10) and Enembe/Isithebe Link Road (Ward 12) to be constructed and upgraded by 30 June 2021 | N/A | N/A | 0.8km | 6762817.44 | MIG | N/A | N/A | N/A | N/A | N/A | N/A | Award letter/ progress report | 10, 12 | TSID DIRECTOR | No adjustment
BSD 02 | 12 |  |  |  |  | Percentage | 50% completion of construction for sidewalks at Hlomendlini wards 4 by 30 June 2021 | N/A | N/A | 50% | 1300000 | Municipal | N/A | N/A | N/A | 50% (Construction) | N/A | N/A | Progress report | 4 | TSID DIRECTOR | New KPI
BSD 02 | 13 |  |  |  |  | Percentage | Percentage of upgrade of 6.85kms for the Rural Road Upgrade Phase 3(A, B & C)in wards 2, 3 & 12 by 30 June 2021 | N/A | N/A | 100% | 1081757.69 | MIG | N/A | N/A | N/A | 100% Construction completion | N/A | N/A | Progress report/ Practical Completion certificate | 2, 3 & 12 | TSID DIRECTOR | Changed quarterly target date to the 4th quarter, construction completion.
BSD 02 | 14 |  |  |  |  | Percentage | Percentage of contractor appointment to be rehabilitated at Stratton Circle in ward 3 by 30 June 2021 | N/A | N/A | 100% | 1037741.12 | Municipal | N/A | N/A | N/A | 100% (Award letter) | N/A | N/A | Award letter | 3 | TSID DIRECTOR | New KPI
BSD 02 | 15 |  |  |  |  | Percentage | Percentage of contractor appointment to be rehabilitated at Richard Circle in ward 3 by 30 June 2021 | N/A | N/A | 100% | 1086455.55 | Municipal | N/A | N/A | N/A | 100% (Award letter) | N/A | N/A | Award letter | 3 | TSID DIRECTOR | New KPI
BSD 02 | 16 |  |  |  |  | Percentage | Percentage of contractor appointment to be rehabilitated at Mathews Road in ward 3 by 30 June 2021 | N/A | N/A | 100% | 1035511.75 | Municipal | N/A | N/A | N/A | 100% (Award letter) | N/A | N/A | Award letter | 3 | TSID DIRECTOR | New KPI
BSD 02 | 17 |  |  |  |  | Percentage | Percentage of planning and design stage for the Link Bridge between Highview and Hlomendlini in Ward 3 & 4 by 30 June 2021 | N/A | N/A | 100% | 860124.82 | Municipal | N/A | N/A | N/A | 100% (Design) | N/A | N/A | Detailed design | 3 & 4 | TSID DIRECTOR | New KPI
BSD 02 | 18 |  |  |  |  | Number | Number of m2 potholes repaired in wards 2,3,4,7,10,12,13,14,15 on urban roads by 30 June 2021 | 1317.76 m² | 682.24 m² | 3000m² | 1500000 | Municipal | 600m² | 1000m² | 1000m² | 400m² | N/A | N/A | Measurement Reports | 2,3,4,7,10,12,13,14,15. | TSID DIRECTOR | No adjustment
BSD 02 | 19 |  |  |  |  | Number | Number of guard rails to be constructed in ward 4, 6 and 10 by 31 March 2021 | Not achieved | 300m | 300m | 250000 | Municipal | N/A | N/A | 300m | N/A | N/A | N/A | Completion Certificate | 4,6,10 | TSID DIRECTOR | No adjustment
BSD 02 | 20 |  |  |  |  | Number | Number of kerbs and concrete channel to be constructed in wards 4,6 and 10 by 30 June 2021 | Not achieved | 250m | 200m | 50000 | Municipal | N/A | N/A | N/A | 250m | N/A | N/A | Completion Certificate | 4,6,10 | TSID DIRECTOR | Change targets to 250m on the 4th quarter. And POE to Completion Certificate.
BSD 02 | 21 |  |  |  |  | Number | Number of headwalls to be constructed in wards 1,2,3,4,5,6,7,8,9,10,11,12,16,17,18 by 31 March 2021 | Not achieved | 25 | 25 | 400000 | Municipal | N/A | N/A | 25 | N/A | N/A | N/A | Completion Certificate | 1,2,3,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR | Adjusted 25 to the 3rd quarter, 25 headwalls were over formal quotation which is R200 000. Under the amount, the unit could manage to do 15 and 10 will be done in the 3rd quarter. To be recognized as achieve 25 will be moved.
BSD 02 | 22 |  |  |  |  | Number | Number of kilometres of rural gravel roads repaired and maintained in-house in wards 1,2,4,5,6,7,8,9,10,11,12,16,17,18 by 30 June 2021 | 324.9 km | None | 250 km | 2000000 | Municipal | 50km | 40km | 80km | 80km | N/A | N/A | Measurement Reports | 1,2,4,5,6,7,8,9,10,11,12,16,17,18. | TSID DIRECTOR | No adjustment
BSD 02 | 23 |  |  |  |  | Percentage | Percentage of construction for Highview Park Stormwater modification in ward 3 by 30 June 2021 | N/A | N/A | 50% | 800000 | Municipal | N/A | N/A | N/A | 50% (Construction) | N/A | N/A | Progress report | 3 | TSID DIRECTOR | Changed the KPI target to 50% construction
BSD 02 | 24 |  |  |  |  | Number | Number of speed humps constructed in wards 3,7, 13, 14 and 15 by 31 December 2020 | Not achieved | 15 | 15 | 300000 | Municipal | N/A | 15 | N/A | N/A | N/A | N/A | Completion Certificate | 3,7,13,14,15. | TSID DIRECTOR | No adjustment
BSD 02 | 25 |  |  |  |  | Date | Date of Installation of 30 road signs and repainting of 15km of road markings to completed in ward 3, 4, 7, 13, 14 and 15 by the 31 March 2021 | Not achieved | 10 | 2021-03-31 | 400000 | Municipal | N/A | N/A | 2021-03-31 | N/A | N/A | N/A | Completion Certificate | 3,4,7,13,14,15. | TSID DIRECTOR | No adjustment
BSD 02 | 26 |  |  |  |  | Percentage | Percentage of contractor appointment of overlaying of top suface in Spar parking area in Ward 3 by 30 June 2021 | N/A | N/A | 100% | 700000 | Municipal | N/A | N/A | N/A | 100% (Award letter to contractor) | N/A | N/A | Award letter | 3 | TSID DIRECTOR | Change KPI to 100% award letter to contractor on the 4th quarter and POE to award letter
BSD 02 | 27 |  |  |  |  | Number | Number of installed street name signage in ward 3, 7 and 13 by 31 March 2021 | N/A | N/A | 30 | 130000 | Municipal | N/A | N/A | 30 | N/A | N/A | N/A | Measurement Reports | 3,7,13 | TSID DIRECTOR | No adjustment
BSD 07 | 28 |  | PROVIDING AND FACILITATING ACCESS TO SOCIAL SERVICES AND FACILITIES |  | Facilitate the provision of new community facilities | Percentage | Percentage of contractor appointment and the completion of construction for the swimming pool in ward 15 by 30 June 2021 | Not achieved | 100% (tender award) | 100% | 2870207.52 | MIG | 100% (tender award) | N/A | N/A | 100% Construction completion | N/A | N/A | Tender award letter/ Practical Completion Certificate | 15 | TSID DIRECTOR | No adjustment
BSD 07 | 29 |  |  |  |  | Percentage | Percentage of Planning stage for stage 1-3 (Registration and Detailed design) for the sports field in Hlomendlini in Ward 4 by 30 June 2021 | N/A | N/A | 100% | 500000 | MIG | N/A | N/A | 50 % (Notification of Registration (NOR) with MIG) | 100 % (Advertise) | N/A | N/A | Copy of the NOR letter from COGTA. Copy of advert. | 4 | TSID DIRECTOR | Brought forward NOR notification to 3rd quarter. Added adverting by June 4th quarter
BSD 07 | 30 |  |  |  |  | Percentage | Percentage of contractor appointment and the completion of construction for the sports field in Enembe in Ward 5 by 30 June 2021 | N/A | N/A | 100% | 6000000 | MIG | 50% (tender award) | N/A | N/A | 50% Construction completion | N/A | N/A | Tender award letter/ Practical Completion Certificate | 5 | TSID DIRECTOR | No adjustment
BSD 07 | 31 |  |  |  |  | Date | Date of upgrading of Love Life centre in ward 7 by 30 September 2020 | N/A | N/A | 2020-09-30 | 450000 | Municipal | 2020-09-30 | N/A | N/A | N/A | N/A | N/A | Completion Certificate | 7 | TSID DIRECTOR | No adjustment
BSD 07 | 32 |  |  |  |  | Percentage | 50% percent construction progress and appointment of the contractor for construction for DLTC phase 1 by 30 June 2021 | N/A | N/A | 100% | 4000000 | Municipal | 50% (Award letter to contractor) | N/A | N/A | 100 % (Construction) | N/A | N/A | Award Letter | Ward 3 | TSID DIRECTOR | No adjustment
BSD 07 | 33 |  |  |  |  | Percentage | Percentage of contractor appointment and the completion of construction for the Community Hall in Ward 13 by 30 June 2021 | N/A | N/A | 100% | 10000000 | MIG | N/A | N/A | N/A | 100% (Award letter to contractor) | N/A | N/A | Award Letter | Ward 13 | TSID DIRECTOR | New KPI
MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM 01 | 34 | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | TO DEVELOP A SUSTAINABLE AND EFFICIENT MUNICIPALITY BASED ON SOUND FINANCIAL MANAGEMENT | Ensure a financially viable municipality | Ensure a constant and accurate financial reporting | Number | Number of quarterly risk reports by 30 June 2021 | 4 | None | 2 | N/A | N/A | N/A | N/A | 1 | 1 | N/A | N/A | Attendence register, updated risk register and/or letter of acknowledgent | N/A | TSID DIRECTOR | No adjustment
MFVM 02 | 35 |  |  |  | Improve audit opinion | Number | Number of quarterly review of A.G Action Plan by council by 30 June 2021 | 2 | 2 | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | Council resolution adopting the quarterly reviewed action plan | N/A | TSID DIRECTOR | No adjustment
MFVM 02 | 36 |  |  |  |  | Number | Number of Quarterly Internal Audit Responses provided to Internal Audit Unit by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID DIRECTOR | No adjustment
MFVM 06 | 37 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of 12 Cubic Meter Truck by 31 March 2021 | N/A | N/A | 2021-03-31 | 2500000 | N/A | N.A | N/A | N/A | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR | No adjustment
MFVM 06 | 38 |  |  |  | Ensure that the municipality acquires goods and services in terms of SCM regulations | Date | Date of procurement of a 2 x 4x4 TLBs by 30 June 2021 | N/A | N/A | 2021-06-30 | 2800000 | Municipal | N.A | N/A | N/A | 2021-06-30 | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR | New KPI
MFVM 06 | 39 |  |  |  |  | Date | Date of procurement of a 6-wheel grader by 30 June 2021 | N/A | N/A | 2021-06-30 | 5500000 | Municipal | N.A | N/A | N/A | 2021-06-30 | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR | New KPI
MFVM 06 | 40 |  |  |  |  | Date | Date of procurement of a Tar Mixer by 31 December 2020 | N/A | N/A | 2020-12-31 | 250000 | N/A | N.A | 2020-12-31 | N/A | N/A | N/A | N/A | copy of invoice | N/A | TSID DIRECTOR | No adjustment
MFVM 07 | 41 |  |  |  | Ensure IDP alligned to financial planning | Date | Date of completing draft Departmental Budget estimate document by 31 March 2021 | 2020-03-03 | None | 2021-03-31 | N/A | N/A | N/A | N/A | 2021-03-31 | N/A | N/A | N/A | Draft budget estimate document | N/A | TSID DIRECTOR | No adjustment
MFVM 04 | 42 |  |  |  | Effectively and efficiently manage the expenditure of the municipality | Percentage | Percentage of expenditure on INEP funding by 30 June 2021 | N/A | N/A | 100% | 5000000 | INEP | 15% | 35% | 60% | 100% | N/A | N/A | Signed Report of Expenditure by the Department | N/A | TSID DIRECTOR | No adjustment
MFVM 04 | 43 |  |  |  |  | Percentage | Percentage of expenditure on MIG funding by 30 June 2021 | 99.9% | None | 100% | 35150000 | MIG | 19% | 41% | 66% | 100% | N/A | N/A | MIG Certificate of Expenditure and revenue | N/A | TSID DIRECTOR | No adjustment
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
GGPP 02 | 44 | Good governance and public participation | Ensure partcipative, transparent and accountable governance | Ensure participative, transparent and accountable governance | Ensure the existence and functionality of the public participation structures | Number | Number of quarterly District IGR meetings attended by 30 June 2021 | 1 | 3 | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | Attendence register | N/A | TSID DIRECTOR | No adjustment
MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID 01 | 45 | Municipal transformation and institutional development | PROVISION OF EFFECTIVE, EFFICIENT, TRANSPARENT AND ACCOUNTABLE LEADERSHIP | Creating a conducive working environment | Maintain and improve the municipal policies | Date | Date of the development of the Building and Community Facilities maintenance plan by 30 June 2021 | N/A | N/A | 2021-06-30 | 200000 | Municipal | N/A | N/A | N/A | 2021-06-30 | N/A | N/A | Draft of Building and Community services plan. | N/A | TSID DIRECTOR | No adjustment
MTID 02 | 46 |  |  |  | Ensure effective and efficient human resource management | Date | Date of submission of the departmental Organogram to Corporate Services Department for inclusion in the overall municipal organogram by 28 February 2021 | 2020-02-24 | None | 2021-02-28 | N/A | N/A | N/A | N/A | 2021-02-28 | N/A | N/A | N/A | Draft Organogram and Transmittal to CS/ Council resolution | N/A | TSID DIRECTOR | No adjustment
MTID 06 | 47 |  |  |  | Maintain and improve municipal buildings and assets | Date | Date of partitioning of the Council Chamber by 30 April 2021 | 2019-12-31 | N/A | 2021-04-30 | 600000 | Municipal | N/A | N/A | N/A | 2021-04-30 | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR | Changed date of completion to 30 April 2021
MTID 06 | 48 |  |  |  |  | Date | Date of fencing and gates at the Municipal offices (Main) by 31 March 2021 | N/A | N/A | 2021-03-31 | 250000 | Municipal | N/A | N/A | 2021-03-31 | N/A | N/A | N/A | Practical completion certificate | 3 | TSID DIRECTOR | No adjustment
MTID 06 | 49 |  |  |  |  | Percentage | Percentage of contractor appointment for construction of guardhouses around Municipal buildings by 30 June 2021 | N/A | N/A | 100% | 1800000 | Municipal | N/A | N/A | N/A | 100% (Award letter) | N/A | N/A | Award letter | 3 | TSID DIRECTOR | New KPI
MTID 06 | 50 |  |  |  |  | Percentage | Percentage of design for the Workshop extension at Technical Services by 30 June 2021 | N/A | N/A | 100% | 1300000 | Municipal | N/A | N/A | N/A | 100% | N/A | N/A | Award letter and detailed design | 3 | TSID DIRECTOR | New KPI
MTID 06 | 51 |  |  |  |  | Number | Number of Municipal Plant and Equipment Serviced by 31 March 2021 | 4 | None | 4 | 3500000 | Municipal | N/A | N/A | 4 | N/A | N/A | N/A | Job Cards signed by Mechanic | N/A | TSID DIRECTOR | No adjustment
MTID 06 | 52 |  |  |  |  | Number | Number of Municipal Truck's COF and serviced by 30 June 2021 | 11 | None | 11 | 750000 | Municipal | 3 | 2 | 1 | 5 | N/A | N/A | COF Certificate with Job Card | N/A | TSID DIRECTOR | No adjustment
MTID 04 | 53 |  |  |  | Improve performance | Number | Number of monthly progress reports on implementation of performance plans by managers submitted to HOD's by 30 June 2021 | 12 | None | 12 | N/A | N/A | 3 | 3 | 3 | 3 | N/A | N/A | Monthly performance report | N/A | TSID/DIRECTOR TSID | No adjustment
MTID 04 | 54 |  |  |  |  | Date | Date of submission of manager's performance plan to HOD by 31 August 2020 | 2019-08-31 | N/A | 2020-08-31 | N/A | N/A | 2020-08-31 | N/A | N/A | N/A | N/A | N/A | Signed Manager's Performance Plan | N/A | TSID/DIRECTOR TSID | No adjustment
MTID 04 | [5 empty] | Number | Number of completed quarterly PMS information (POE file and signed scorecard) to PMS unit by 30 June 2021 | 4 | None | 4 | N/A | N/A | 1 | 1 | 1 | 1 | N/A | N/A | letter of acknowledgement from the unit | N/A | TSID/DIRECTOR TSID | Remove KPI
LOCAL ECONOMIC DEVELOPMENT
LED 02 |  | LOCAL ECONOMIC DEVELOPMENT | Promoting and facilitating human development | Achieve a holistic human development and capacitation for the realisation of a skilled employable workforce | Improve the community skills base | Date | Date of ensuring that all qualifying tender specifications provide for subcontracting opportunities for emerging local contractors as and when a tender document is being compiled by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | 2020-06-30 | N/A | N/A | Copy of the signed/ published tender advert. | N/A | TSID/DIRECTOR TSID | Remove KPI
LED 02 | [5 empty] | Date | Date of ensuring that project implementation includes employment of local labour as and when projects are implemented by 30 June 2021 | N/A | N/A | 2020-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Reports for projects under construction. | N/A | TSID/DIRECTOR TSID | Remove KPI
[19 empty] | Signature: | …………………………………..
KP GUMEDE
Director: TSID
Note on L47: Khetha Gumede: Correct the budget