## EDPHS 20222023
ADJUSTED 2022/23 ECONOMIC DEVELOPMENT, PLANNING AND HUMAN SETTELEMENTS SCORECARD
IDP REF NO | KPI NO. | NATIONAL KEY PERFORMANCE AREA ( BACK TO BASIC PRINCIPLES) | Strategic goals | Strategic objectives | Strategies 2022-23 | Unit of measurement | Key Performance Indicator | BASELINE | BACKLOG | Annual Target | Annual budget | Quarter 1 |  | Quarter 2 |  | Quarter 3 | Quarter 3 | Quarter 4 | Achieved/Not achieved | Reason for variance | Corrective Measures |  | Reason for Variance | Corrective measures | Reason for Variences | Corrective Measures | Portfolio of Evidence | WARD | Responsible Manager/ Person | Adjustments
[12 empty] | Target | Actual | Target | Actual | Target |  | Target |  |  |  | Aactual
BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
BSD 03 | 1 | BASIC SERVICE DELIVERY | Universal access to basic services and infrastructure development by 2030 | To improve access to all infrastructure and services | Facilitate the reduction of the housing backlog | Number | Number of new RDP houses constructed in combined Wards 1, 2, 9, 8, 11, 16,17 and 18 by 30 June 2023 | new | None | 200 | Externally Funded | N/A | 1 | 50 | 1 | N/A | 1 | 150 | N/A | N/A | N/A | 2 | N/A | N/A | N/A | N/A | Happy letters | 1; 2; 8; 9; 11; 12; 16,17 and 18 | EDPHS (Director) | The annual target initially was 400. However, due to projects on hold in ward 10 as well as no fund allocated for ward 12 project, the EDPHS adjusted the annual target to 200. These projects are under the Inyoni housing projects.
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
GGPP 01 | 2 |  |  | Ensure that all legislated council structures meetings sit | Improve public participation | Number | Number of quarterly audit and performance committee meetings attended by 30 June 2023 | None | None | 4 | N/A | 1 |  | 1 | 1 | 1 |  | 1 | [8 empty] | Attendance Registers | 3 | EDPHS (Director)
GGPP 02 | 3 |  |  |  |  | Number | Number of quartely cluster war-rooms reports submitted to OMM by 30 June 2023 (Ward 5 & 14) | N/A | N/A | 4 | N/A | 1 |  | 1 | 1 | 1 |  | 1 | [8 empty] | Attendance register | 5.14 | EDPHS (Director)
GGPP 05 | 4 |  |  |  |  | Date | Date of adoption of the 2023/24 IDP, Budget and PMS Process Plan by 31 August 2022 | N/A | N/A | 2022-08-31 | N/A | 2022-08-31 |  | N/A |  | N/A |  | N/A | [8 empty] | Council Resolution | 18 Wards | EDPHS (Director)
GGPP 05 | 5 |  |  |  |  | Date | Date of approval and adoption of the 2023/24 IDP by Council by 31 May 2023 | New | 2 | 2023-05-31 | R150 000,00 | N/A | N/A | N/A | N/A | N/A | 1 | 2023-05-31 | N/A | N/A | N/A | 1 | N/A | N/A | N/A | N/A | Council Resolutions | 18 Wards | EDPHS (Director)
GGPP 05 | 6 |  |  |  |  | Number | Number of quarterly Performance reports submitted to EDPHS Portfolio Committee by 30 June 2023 | None | None | 4 | N/A | 1 |  | 1 |  | 1 |  | 1 | [8 empty] | Minutes of EDPHS Portfolio Committee | N/A | EDPHS (Director)
GGPP06 | 7 |  |  |  |  | Number | Number of risk mitigation strategies implemeneted by EDPHS Department by 30 June 2023 | New | None | 35 | N/A | 11 |  | 8 |  | 8 |  | 8 | [8 empty] | Acknowledgement Letter and Quarterly risk mitigation action plan | N/A | EDPHS (Director)
GGPP06 | 8 |  |  |  |  | Number | Number of risk progress reports submitted to risk management unit by 30 June 2023 | New | None | 4 | N/A | 1 |  | 1 |  | 1 |  | 1 | [8 empty] | Acknowledgement Letter and Quarterly risk mitigation progress report | N/A | EDPHS (Director)
GGPP 06 | 9 |  |  |  |  | Number | Number of days for management to respond to Internal Audit Unit queries raised by 30 June 2023 | New | None | 3 days' | N/A | 3 days' | 3 days' | 3 days' | 3 days' | 3 days' | 3 days' | 3 days' | [8 empty] | Acknoweledgement Letters | N/A | EDPHS (Director)
GGPP 06 | 10 |  |  |  |  | Number | Number of days for management to respond to request for information and Audit Queries raised by Auditor General by 31 December 2022 | New | None | 3 days' | N/A | 3 days' | 3 days' | 3 days' | 3 days' | N/A | 3 days' | N/A | [8 empty] | Tracking Tool | N/A | EDPHS (Director)
LOCAL ECONOMIC DEVELOPMENT
LED 02 | 11 | LOCAL ECONOMIC DEVELOPMENT | Facilitate the creation of job opportunities | Achieve a holistic human development and capacitation for the realisation of skilled and employable workforce | Unlock the agricultural potential | Number | Number of farmers supported with seedlings, and animal feeds by 30 June 2023 | New | None | 9 | 200000 | n/a |  | 3 |  | 3 |  | 3 | [8 empty] | Aknowledgement letter | 1,2,4,5,6,8,9,10,11,12,16,17,18 | EDPHS (Director)
LED 02 | 12 |  |  |  | Facilitate SMME development | Number | Number of SMME Supported (Quick Wins) in all Wards by 30 June 2023 | New | none | 36 | R1 000 000,00 | N/A |  | 10 | N/A | 13 |  | 13 | [8 empty] | Aknowledgement letter | All Wards (18) | EDPHS (Director)
| 17 | [26 empty] | All Wards (18) | EDPHS (Director)
LED 07 | 13 |  |  |  | Facilitate SMME development | Number | Number of bi-annual training provided intended to improving the business skills in particular SMME's by 30 June 2023 | 2 | None | 2 | R20 000,00 | N/A | N/A | 1 | 1 | N/A |  | 1 |  |  |  | 1 | N/A | N/A | N/A | N/A | Attendance register and certificates | All | EDPHS (Director)
LED 07 | 14 |  |  |  |  | Date | Date of facilitating the development of Ngwenya Nature Reserve by 30 June 2023 | New |  | 2023-06-30 | 480000 | N/A | N/A | N/A | N/A | N/A |  | 2023-06-30 | [8 empty] | Copy of Advert and appointment letter | 3 | EDPHS (Director)
| 17 | [26 empty] | 1,2 | EDPHS (Director)
LED 07 | 15 |  |  |  |  | Number | Number of quartely Emerging Entreprenuers supported on the entrepreneur support programme by 30 June 2023 | 4 | None | 4 | 300000 | N/A | 2 | 2 | 0 | 1 | 2 | 1 | N/A | N/A | N/A | 0 | Delayed in the approval of the approved businesses to be assisted through Mayoral Covid 19 Business Support Programme | Approved businesses have been sorted and submitted to SCM for procurement processes. | N/A | N/A | List the entreprenuers supported and report | All | EDPHS (Director)
LED 07 | 16 |  |  |  |  | Number | Number of quartely business compliance inspections conducted by 30 June 2023 | 4 | None | 4 | Internal Resources | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | 2 | N/A | N/A | N/A | N/A | Attendance Register (A list of various B C workshops conducted) | All | EDPHS (Director)
LED 04 | 17 |  |  |  | Implement the EPWP programme | Number | Number of jobs sustained through construction of RDP housing projects by 30 June 2023 | New | new | 400 | Internal Resources | 100 | 1 | 100 | 1 | 100 |  | 100 |  |  |  | 2 | N/A | N/A | N/A | N/A | Beneficiary Register | 1,8,10,11,12,16,17&18 | EDPHS (Director)
LED 06 | 18 |  |  |  | Unlock the agricultural potential | Date | Date of hosting business of Fair by 31 March 2023 | N/A | N/A | 2023-03-31 | R200 000,00 | N/A | N/A | N/A | N/A | 2023-03-31 |  | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A | Attendance Register | All | EDPHS (Director)
LED 07 | 19 |  |  |  | Strategic planning for LED | Number | Number of quarterly reports on the implementation of Vuthela LED programme submitted to EXCO by 30 June 2023 | 4 | None | 4 | R300 000,00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | 2 |  | N/A | N/A | N/A | Reports/EXCO resolution | All | EDPHS (Director)
MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM 01 | 20 | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | To develop a sustainable and efficient municipality based on sound financial management | To enhance strategic and leadership accountability | Ensure a constant and accurate financial reporting | Percentage | Percentage of operational budget spent by 30 June 2023 | 100% | N/A | 100% | 15860766 | 5% |  | 25% |  | 75% |  | 100% | [8 empty] | Management account | N/A | EDPHS (Director)
MFVM 02 | 21 |  |  |  | Ensure the existence of updated finance management strategies | Rands | amount of quartely of expenditure on overtime kept within allocated budget by 30 June 2023 | New | None | 30000 | 30000 | 7500 |  | 7500 |  | 7500 |  | 7500 |  |  |  | 2 | N/A | N/A | N/A | N/A | Report from finance showing expenditure on overtime | All | EDPHS (Director)
MFVM 06 | 22 |  |  |  | Ensure that the municipality acquires goods and services in terms of supply chain regulations | Date | Date of procurement of equipment for fisherman by 30 June 2023 | New | New | 2022-12-31 | 200000 | N/A | N/A | N/A | N/A | N/A |  | 2023-06-30 | [8 empty] | Delivery note/acknowledgement letter | All | EDPHS (Director) | Reviewed the KPI to state the procurement of equipment as opposed to coldroom, this is on the basis the fishermen have changed their priorities
MFVM 05 | 23 |  |  |  | Manage and increase the municipal revenue base | Rands | Amount of revenue collected as per submitted town planning applications, business license, building plans and rental collection from Informal Traders Stalls by 30 June 2023 | New | New | R100 000,00 | Internal Resources | R10 000,00 | 13059.36 | R30,000,00 | 27198.94 | R30,000,00 | 20000 | R30,000,00 | N/A | N/A | N/A | R27 198,94 | N/A | N/A | N/A | N/A | Ledge Spread Sheet from Finance | All | EDPHS (Director)
SPATIAL RATIONAL AND ENVIRONMENTAL MANAGEMENT/CROSS-CUTTING MEASURES
SREM 01 | 24 | SPATIONAL RATIONAL AND ENVIRONMENTAL MANAGEMENT/ CROSS-CUTTING MEASURES | Promoting and facilitating environmental protection and sustainable spatial planning | CBD Regenaration | Creating government precinct with efficient space for public facilities and services | Percentage | Percentage of building plans approved within 60 days | New | New | 100% of building plans submitted approved within 60 days of submission (applies to building plans with no issues) | Internal Resources | 100% |  | 100% |  | 100% |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Date and time stamped data, Sequential List of building plans received, sequential list of building plans processed within 60 days letters to applicants | N/A+AC36:AE36 | EDPHS (Director) | KPI has been revised to be realistic and measurable
SREM 03 | 25 |  |  | Facilitate a creation of a disaster-ready community | Provide a framework for the spatial vision and form of Municipality | Date | Date of Review and final adoption of Spatial Development Framework by Council by 31 May 2023 | Draft SDF | N/A | 2023-05-31 | Internal Resources | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Council Resolution | All | EDPHS (Director)
SREM 02 | 26 |  |  | Ensure an integrated and alligned development planning | Ensure proper development | Date | Date of Draft EIA scoping report for the Dokodweni Beach by 30 June 2023 | N/A | N/A | 2023-06-30 | 200000 | N/A | N/A | N/A | N/A | N/A |  | 2023-06-30 |  |  |  | N/A |  |  | N/A | N/A | Draft EIA Report / Attendance Register of PSC meetings | 1 | EDPHS (Director)
SREM 02 | 27 |  |  |  |  | Date | Date of approval of agricultural sector plan by 30 June 2023 | New | n/a | 30-Jun-23 | R400 000,00 | N/A |  | N/A | N/A | N/A |  | 30-Jun-23 | [8 empty] | Council Resolution | All Wards
SREM 02 | 28 |  |  |  |  | Date | Date of preparation and adoption of Precinct Plans for Mandeni Victor Square and Sundumbili CBD (Town) area by 31 March 2023 | New | New | 2023-03-31 | R800 000,00 | N/A | N/A | N/A | N/A | 2023-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Council Resolution | 3,7 | EDPHS (Director)
MTID 04 | 29 | MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT | PROVISION OF EFFECTIVE, EFFICIENT, TRANSPARENT AND ACCOUNTABLE LEADERSHIP | CREATING A CONDUCIVE WORKING ENVIRONMENT | Improve performance | Date | Date of submission of managers performance plans to HOD's by 31 August 2022 | 2020-08-30 | None | 2022-08-31 | Internal Resources | 2022-08-31 | 2020-08-20 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | 2020-08-20 | N/A | N/A | N/A | N/A | Manager's Performance Plan's | N/A | EDPHS (Director)
MTID 04 | 30 |  |  |  |  | Number | Number of progress reports on implementation of performance plans by managers submitted to HOD's by 30 June 2023 | 36 | None | 36 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | N/A | N/A | N/A | 18 | N/A | N/A | N/A | N/A | PMS monthly progress reports | N/A | EDPHS (Director)
ECONOMIC DEVELOPMENT, PLANNING AND HUMAN SETTLEMENTS
APPROVED BY DIRECTOR EDPHS: MR. W.D. MBONGWA
SIGNATURE